## BuspassManagement Debug Report
BUG ID | Type | Feature | Description | Priority | Screenshots & Attachments | Error | Status | Found At | Updated by | Created At | Fixed at
BUG-001 | Bug | Loading Database Configuration | Database configuration does not loads from command line argument. | High | https://snipboard.io/kbJC4q.jpg | java.lang.ArrayIndexOutOfBoundsException | Fixed | App.java:17 | Aman Srivastava | 2023-02-17 18:35 | 2023-02-17 18:36
BUG-002 | Bug | Main Menu | Main Menu is not loading from another java class as its object is given null | High | https://snipboard.io/Ap9uks.jpg | java.lang.NullPointerException | Fixed | App.java:20 | Aman Srivastava | 2023-02-17 18:50 | 2023-02-17 18:50
BUG-003 | Bug | Database Connectivity | Cannot make connection with JDBC as it was configured for My-SQL so changed it to MS-SQL Server in pom.xml where | High | https://snipboard.io/EshVbF.jpg | com.mysql.cj.jdbc.exceptions.CommunicationsException | Fixed | DB.java and pom dependency | Aman Srivastava | 2023-02-17 18:55 | 2023-02-17 19:10
BUG-004 | Bug | Loading Database Configuration | Database configuration file cannot be read as filepath is different and MY-SQL dependency is present, also DB.java is configured for MY-SQL | High | https://snipboard.io/EshVbF.jpg | com.mysql.cj.jdbc.exceptions.CommunicationsException | Fixed | DB.java and pom dependency | Aman Srivastava | 2023-02-17 19:17 | 2023-02-17 19:29
BUG-005 | Bug | Loading AdminMenu and UserMenu | Cannot load AdminMenu and UserMenu from MenuFactory class | High | https://snipboard.io/fAyEuz.jpg | Throwing Catch error | Fixed | MenuFactory.java | Aman Srivastava | 2023-02-17 19:48 | 2023-02-17 19:59
BUG-006 | Bug | Loading UserMenu Instance | Cannot load UserMenu Instance as no object is initiated in UserMenu class under singelton design pattern | High | https://snipboard.io/9RByKN.jpg | java.lang.Error | Fixed | at com.amazon.buspassmanagement.UserMenu.getInstance(UserMenu.java:15) at com.amazon.buspassmanagement.MenuFactory.getMenu(MenuFactory.java:10) at com.amazon.buspassmanagement.Menu.showMainMenu(Menu.java:43) at com.amazon.buspassmanagement.App.main(App.java:19) | Aman Srivastava | 2023-02-17 20:02 | 2023-02-17 20:06
BUG-007 | Bug | Login User | Cannot load user details from database in User object under loginUser method | High | https://snipboard.io/lihAQX.jpg | Throwing Catch error: Authentication Failed | Fixed | AuthenticationService.java | Aman Srivastava | 2023-02-17 20:54 | 2023-02-17 20:56
BUG-008 | Bug | Login Admin | Cannot load admin user details from database in password as it is not getting hashed | High | https://snipboard.io/VvpTmy.jpg | Throwing Error: Invalid Credentials, Try Again | Fixed | AdminMenu.java | Aman Srivastava | 2023-02-18 13:05 | 2023-02-18 13:10
BUG-009 | Bug | Apply for BusPass | Cannot apply for BusPass because of foreign key constraints of User ID from Users table since it should match with id when applying for busspass- at line 35 in BusPassService.java | High | https://snipboard.io/cfnDOH.jpg | com.microsoft.sqlserver.jdbc.SQLServerException: The INSERT statement conflicted with the FOREIGN KEY constraint "buspass_id_fk". The conflict occurred in database "buspassdebugdb", table "dbo.Users", column 'id' | Fixed | BusPassService.java | Aman Srivastava | 2023-02-18 13:15 | 2023-02-18 13:23
BUG-010 | Bug | Approving Bus Pass | Even after approving the bus pass valid till date is not incremented for 1 year as calendar.add line at 89 is commented | High | https://snipboard.io/VdtoQL.jpg | Logical Error | Fixed | BusPassService.java | Aman Srivastava | 2023-02-18 13:29 | 2023-02-18 13:31